## Slide 1: Reference Model (JIRA/QMetry) Migration & Rollout – Communication Plan to cover migration planning and trainings

## Slide 2: Overview
As part of the rollout and transition to the Atlassian/Jira Reference Model to all Dealertrack Solution Lines, this document captures important communication events with dates associated with the Migration Planning and Tools Trainings
This document is meant for communication with every one who is directly associated with the Roll out , Mandatory Nominees (Train the Trainers*) and also for any who is interested in getting trained. Hence the primary audience to read this plan are
  Sponsors/Steering Committee
  Solution Group Engineering Head and QA Manager
  Solution Group Business Head
  Solution Group Infrastructure, Change Control Lead
  Each Solution Line Project Manager nominated to plan and execute this rollout
  HQ and Local Admins
  Train the Trainer - Mandatory Participants who needs to be identified by the Solution Line Project Manager
The training will utilize Train the Trainer approach hence nomination for the following are expected to be in place by Oct 17th
  Product Owner/BU Rep (Representative)
  PM, Scrum Master Rep
  Development Rep
  QA Rep
  Change Control Rep
  Infrastructure Rep
Apart from the Train the Trainer Nominees the trainings are open for any one to join!
Please review Important notes regarding the training logistics and etiquettes in the last slide

## Slide 3: Program Planning Communication – Key Dates
 | Mandatory Participants (Train the Trainer Nominee per BU ) | Secondary Participants | Objective | Date
Migration and Rollout Kick-Off | Solution Team PMs, Admins, Key Stakeholders (Business and Technology), Sponsor | Senior Leadership | Provide clarity on reference Model Rollout Program objective and timelines | 7th Oct 2013
Migration Release Planning Guidelines Walkthrough | HQ Program Manger, Solution Team PMs, Central and Local Admin | Senior Leadership from HQ and BU | Provide guidelines to business unit groups on how to plan for and execute Data Migration of current Source system data (User Stories, Requirements, Defects, QA test cases) to the new DT Reference Model: JIRA/Qmetry | 11th Oct 2013
Program Checkpoint Review | Solution Team PMs, Local Admins, Central Admin | Senior Leadership from HQ and BU, Sponsor | Solution PM / Local Admin will present migration release plan for their group for review | 28th Oct 2013
Recurring Standup Calls for Release Planning Status Check / Issue Resolution | Solution Team PMs, Local Admins |  | Solution team reps will provide status updates on status of migration planning and will have opportunity to ask questions on any specific issues | 14th, 16th, 18th 21st, 23rd, 25th Oct 2013
Program Interlock Presentation | Sponsor, Steering Committee, Central Admin, Solution Team Representation (Local Admin, Solution Team PM) |  | Solution PM / Local Admin will present migration release plan for their group for approval from Steering Committee | 4th Nov 2013

## Slide 4: Training Communication – Key Dates
 | Mandatory Participants (Train the Trainer Nominee per BU*) | Secondary Participants | Objective | Date
I Technical Admin Trainings |  |  |  | 
Session #1 : Jira\QMetry : Reference Model Migration Training | Central Admin, Local Admin | Solution Team PMs | Introduction & Context Settings Provide administrators technical walkthrough of the Guidelines document | 9th Oct 2013
Session #1 : Jira\QMetry : Jira Migration | Central Admin, Local Admin | Solution Team PMs | How to migrate data into Jira | 11th Oct 2013
Session #1 : Jira\QMetry : Qmetry Project Administration & Data Migration | Central Admin, Local Admin | Solution Team PMs and QA Managers | Qmetry project administration Qmetry data migration | 15th Oct 2013
II End User Tool Trainings |  |  |  | 
Session # 1 : Tools, Concepts & Methodologies | Nominees from BU Product Owner/BU Rep (Representative) PM,Scrum Master Rep Development Rep QA Rep Change Control Rep Infrastructure Rep Local Admin | Senior Leadership Open for anyone in the roles mentioned in mandatory participants | Introduce the teams with Dealertrack Reference Model & provide an overview of the tools & key concepts | 23rd Oct 2013
Session # 2: Backlog, Scrum Board & Sprints | Same as above | Same as above | How to manage Backlogs, scrum board , and sprints using Jira & green hopper | 30th Oct 2013
Session # 3: Workflows & Transitions ¦ Search, Reporting & Dashboards | Same as above | Same as above | Walkthrough of the workflows that are defined as part of reference model in Jira (Sub-Tasks, Story, Defect,Tech Story, Requirement, etc. Search & Reporting) | 5th Nov 2013
Session # 4: Change & Release Management | Same as above | Same as above | How to create & manage Release ticket for change and release management | 8th Nov 2013
Session # 5: QMetry | Nominees from BU Product Owner/BU Rep (Representative) PM,Scrum Master Rep Development Rep QA Rep Local Admin | Same as above | How to use QMetry and its integration with Jira | 14th Nov 2013
* These participants are mandatory and each BU should nominate at least 1 person in the corresponding roles identified in the column to act as an internal trainer/mentor their group

## Slide 5: Training Communication – Key Dates
 | Participants |  | Objective | Date
III End User Trainings ( Additional Q&A Sessions) |  |  |  | 
Session #1 : End User Training Q&A |  | Open for any one who took training on the Regular Training Slots and has questions | To Answer Questions from End User Training participants on the End User Training Modules Part I ( 40 Minutes) Tools, Concepts & Methodologies Backlog, Scrum Board & Sprints Workflows & Transitions ¦ Search, Reporting & Dashboards Part – II ( 10 Minutes) Change & Release Management Part – II ( 10 Minutes) QMetry | 1st Nov 2013
Session #2 : End User Training Q&A |  | Same as Above | Same as Above | 19th Nov 2013
Session #3 : End User Training Q&A TENTATIVE – Only if there is a need for an additional session |  | Same as Above | Same as Above | 22nd Nov 2013
Important Training Logistics and Etiquettes
Each BU Must nominate their Train the Trainer representative by 17th of Oct 2013
Trainings will be conducted using Go To Meeting Webinar. You would need to register in advance for the training before hand – A URL will be sent in advance in a Meeting invite for you to register
All training sessions will be recorded – Video and Audio and will be hosted at a central place
You can use the recordings after the trainings at your leisure to practice and review.
Please join the training bridge at least 3 minutes before the call. Given the trainings are recorded late joining can cause noise
Each session will have multiple parts (usually 10-15 min) based on topics. There will be a Q&A after each part, please reserve your questions to be raised during the Q&A slot.
Please keep your lines muted unless you have a question during the Q&A slots
In addition to the 8 trainings sessions - 3 for Admin and 5 for End User Training, there will be 3 more Q&A sessions – you can utilize these sessions to ask any additional questions you may have post trainings. Each of these sessions will have 3 parts as described in Section III under trainings. You can choose to join the part that is relevant to you