## Project
| Project Name | KT by Trainer |  |  |  | Planned KT - Date with DealerTrack | KT By | KT Status | Can Support this component? (Y/N) | Resource Name
Type |  |  | Hands On with Trainer | Prod HandsOn | Self | [5 empty] | Comments
Jira | Jira complete Navigation & Agile Board | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Creation of Version \ Releases | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | New Card\Items\Backlog | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Epic\Themes | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Story | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Subtasks | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Technical Task | 0% | 0% | 0% | 0% | 2014-06-30 | Arijit Banerjee | 0% | 0%
Jira | Different issue Types in Jira - How to Customize | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Ranking Issues | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Scheduling and Assigning | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Assigning Issue/Items to Sprint/Release (Drag and Drop) | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Updating Issues fields | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Comment | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Log Work | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Subtasks | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Assign | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Flag | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Log Work | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Classic Planning Board Views | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | a. List | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | b. Cards | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | c. Summary | 0% | 0% | 0% | 0% | 2014-07-01 | Arijit Banerjee | 0% | 0%
Jira | Using Quick Search | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | a. Free-text search | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | b. Term based search | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | c. Browser search | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | d. Board Search | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | Default Board filters | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | 1. Using Classic Board Modes | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | i. Planning Board, Version and Release | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | ii. Task Board, Release and Roles | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | iii. <Chart Board> and Charts | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | iv. <Release Board> and Statistics | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | 1. Project Switching | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | 2. Using Contexts to Filter and Highlight Issues | 0% | 0% | 0% | 0% | 2014-07-02 | Arijit Banerjee | 0% | 0%
Jira | Greenhopper | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | 1. Using Plan Mode | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | 2. Using Work Mode | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | 3. Using Report Mode | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | 4. Working with Sprint | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | a. Creating a Sprint | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | b. Starting a Sprint | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | c. Ending a Sprint | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | d. Releasing a Version | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | e. Editing or Renaming a Sprint | 0% | 0% | 0% | 0% | 2014-06-27 | Kiran M | 100% | 100% | Firoz Khan
Jira | 5. Working with Issues | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | a. Create and View Issue | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | b. Editing an Issue | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | c. Estimating an Issue | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | d. Ranking an Issue | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | e. Transitioning an Issue | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | f. Adding Issue to Sprint | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | g. Removing Issue from the Sprint | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | Jira Issue Details | 0% | 0% | 0% | 0%
Jira | 1. Edit | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 2. Assign/Start/Resolve/Subtask, Description | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 3. More Actions | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | a. Log Work | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | b. Attach Files/Screenshots | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | c. Move, Link, Clone, Delete | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 4. Share | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 5. Views | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 6. Comment | 0% | 0% | 0% | 0% | 2014-06-30 | Kiran M | 100% | 100% | Firoz Khan
Jira | 7. Emailing | 0% | 0% | 0% | 0% | 2014-07-01 | Kiran M | 100% | 100% | Firoz Khan
Jira | Jira Administration - Complete Functional\Technical | 0% | 0% | 0% | 0% | 2014-07-03 | Kiran M | 100% | 100% | Firoz Khan
Jira | Customizaton - Fields\Validations etc | 0% | 0% | 0% | 0% | 2014-07-03 | Kiran M | 100% | 100% | Firoz Khan
Jira | Plugins Concept | 0% | 0% | 0% | 0% | 2014-07-03 | Kiran M | 100% | 100% | Firoz Khan
Jira | Custom Plugins | 0% | 0% | 0% | 0% | 2014-07-03 | Kiran M | 100% | 100% | Firoz Khan
Jira | Workflow In Detail - How to customize | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | Roles & Permissions | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | Dashboards | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | Custom Dashboards | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | Reference Model V2.0 | 0% | 0% | 0% | 0% |  |  |  | 0%
Jira | 1. Issue Types | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | 2. Workflow Schemes | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | 3. Workflow Screens | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | 4. Validations | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | 5. Scripting | 0% | 0% | 0% | 0% | 2014-07-03 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira | Plugin | 0% | 0% | 0% | 0% |  |  |  | 0%
Jira | 1. Plugin concepts | 0% | 0% | 0% | 0% | 2014-07-01 | Kiran M | 100% | 100% | Firoz Khan
Jira | 2. Plugin Modules | 0% | 0% | 0% | 0% | 2014-07-01 | Kiran M | 100% | 100% | Firoz Khan
Jira | 3. Gadgets | 0% | 0% | 0% | 0% | 2014-07-07 | Kiran M | 100% | 100% | Firoz Khan
Jira | 4. Velacity Templeates | 0% | 0% | 0% | 0% | 2014-07-07 | Kiran M | 100% | 100% | Firoz Khan
Jira | 5. Scripting | 0% | 0% | 0% | 0% | 2014-07-07 | Kiran M | 100% | 100% | Firoz Khan
Jira Integration | Salesforce | [7 empty] | 0%
Jira Integration | 1. Configuration on SF | 0% | 0% | 0% | 0% | 2014-07-08 | Arijit Banerjee | 0% | 0% | Firoz Khan
Jira Integration | 2. Plugin for salesforce | 0% | 0% | 0% | 0% | 2014-07-08 | Kiran M | 0% | 0% | Firoz Khan
Jira Integration | 3. Sync between jira and salesforce | 0% | 0% | 0% | 0% | 2014-07-08 | Kiran M | 0% | 0% | Firoz Khan
Jira Integration | Qmetry | [7 empty] | 0%
Jira Integration | 1. Project/Release/Version Mapping | 0% | 0% | 0% | 0% | 2014-07-08 | Arijit Banerjee/Kiran M | 0% | 0% | Firoz Khan
Jira Integration | 2. Integration with Qmetry | 0% | 0% | 0% | 0% | 2014-07-08 | Kiran M | 0% | 0% | Firoz Khan
Jira Integration | 3. Gadgets on Qmetry | 0% | 0% | 0% | 0% | 2014-07-08 | Kiran M | 0% | 0% | Firoz Khan
Jira Integration | Inntoas
Jira Integration | 1. Integration with Inntoas | 0% | 0% | 0% | 0% | 2014-07-09 | Kiran M | 0% |  | Firoz Khan
Jira Integration | 2. Project mapping and sync | 0% | 0% | 0% | 0% | 2014-07-10 | Kiran M | 0% |  | Firoz Khan
Jira Integration | 3. Gadgets on Innotas | 0% | 0% | 0% | 0% | 2014-07-10 | Kiran M | 0% |  | Firoz Khan
Jira Integration | 4. Plugin development | 0% | 0% | 0% | 0% | 2014-07-10 | Kiran M | 0% |  | Firoz Khan
Formulas:
Planned KT - Date with DealerTrack = [Planned KT - Date with DealerTrack, row above]
Note on I1: Author: Includes KT , Self Learning, Clarifications. Should be marked as 100% when this component can be supported independently.
Note on J1: Author: Legend in Green Means : Offshore redy to support the component
Note on D2: Vikas Basra: Self Learning by Ness Resource
Note on E2: Vikas Basra: Should be marked as 100% once the documentation is ready with the required configuration details