## Sheet1
Synergy CRM SF Phase 0a Fusion to SAP/SF Interfaces 5/16-5/18 Production Cutover Required Resources See Production Cutover Plan for specific timelines
Required Resources | Required Availability | Confirmed By | Confirmed Resource and Phone Number | Notes
Fusion Architect - Mike Massimilla | On Call Entire Cutover | Mike M | Not Required | 4/22/14 Mike M will not be available - Team is aware and will work with Srini K
DT.COM - Srini Kanuri (or someone from his team) | On-Call entire time | Srini K | Srini Kanuri 908 565 3494 Mahesh Rangaiah 631 678 3430 Gautam Arora 917 407 6647 Howard Chang 516 640 6948 | 4/22/14 received confirmation from Srini Kanuri - May be on call and not On-Site due to not much required - to confirm
Canada DT.CN - Paul Bird | On Call entire time | Paul Bird | Paul Bird 416.705.4556 | 4/22/14 Paul had originally confirmed available but questioning what is needed
US DB SQLServer and SSIS support - Ralph Padula to assign, worked with Joseph Sohn/Raman Gupta | On-Site entire time | Barbara Robins Ralph Padula | Joseph Sohn 516-724-0200 Barbara Robins 516-477-3843 | 4/22/14 reconfirmed resources with Barbara 4/1/14 as per Ralph Padula, Barbara will coordinate/confirm the resources - we should work with her. As per Barbara, Joseph is the confirmed resource but as per Jomy per a follow-up that he had with Ralph, it may not be Joseph - Jomy is confirming the resource with Ralph The request is to get Joseph Sohn
US Db Hub Support - Ralph Padula to assign – worked with with Susan Camera / Alice Liour | On-Call entire time | Barbara Robins Ralph Padula | Alice Liour: 973-626-2398 Steve Lei | 4/24/14 reconfirmed from Barbara that Alice will be the resource 4/22/14 reconfirmed resources with Barbara 4/1/14 as per Ralph Padula, Barbara will coordinate/confirm the resources - we should work with her. Was Alice but as per Jomy follow-up meeting with Ralph may be someone else - Jomy is confirming the resource with Ralph Oracle - Probably will not be Susan
Canada DB - Fernando Da Silva | On Call entire Cutover | Ralph Padula | Fernando DaSilva 647 224 8408 | 4/24/14 confirmed needed by DT.COM and DB team - sent follow-up email to Fernando to confirm 4/22/14 confirming with Barbara but not noted as required To confirm with Ralph if required
Splunk Admin - Joseph Scordo | On-Call during deployment of Legacy ID interface | Michael Stancampino | Joseph Scordo (516)361-0277 | Check with Mike Verdugo if we need them on call or on site
Infrastructure - Will Tisdale, Joe Trinceri | On Call entire Prod Cutover | Charles Mahlmeister, Will Tisdale | Will Tisdale 516.589.4928 Joseph Trinceri 516-589-4925 | 4/24/14 Will Tisdale confirmed - waiting on confirmation from Joe Trinceri
Infrastructure - Storage/DB - Tom Abrue, Sandeep Chilukuri | On Call entire Prod Cutover | Sandeep, Tom Abrue | Sandeep Chilukuri 516-639-3379 Richard Yang 516-232-3584 | 4/24/14 needed due to have to stop replication of SAP with planned call midnight. May also be needed throughout Sat and Sun if space issues arise
QA – Margaret and/or Helen | On-Site for PVT as prod interfaces deployed | Andrew Quattropani | Helen Rastelli: Cell 917-601-9598 Margaret Valenti: Cell-631-404-8811 | 4/23/14 confirmed Margaret and Helen 3/27/14 Andrew confirmed QA will be available - will get back on specific names. Need QA team to perform PVT after deployment of each interface
Synergy Interface team – Tom W, Jomy, Joanne, Srini, Mike V, Kumar, Suresh, Manish, Kunal, and Harsh | On-site Prod Pre-cutover and cutover | Jomy | Tom Wirth: 516-244-3209 Jomy Molakan: 516-637-9111 Srini Davaluri: 636-234-8052 Mike Verdugo: 908-500-6009 V Kumar: 516-246-1731 Suresh Revuru: 847.373.5748 Manish Rout: 1 936 666 7008 Kunal Buddhdeo: 206-816-9096 Harsh Kolli | Manish on call. Suresh on call
Synergy CRM PM - Joanne Scutaro | On Call pre-cutover. On Site Cutover | Joanne Scutaro | Joanne Scutaro 631-821-5930
Skyvva Support | On Call enter Prod cutover | Sy Pauv | Sy Pauv +855 99 614 715
Salesforce Premier Support | On Call enter Prod cutover |  |  | Email sent
Security - SAP | On Call To support QA PVT Access requirements and building access for Prod cutover | Hector Vale | Hector Vale 347-386-8646 Ramesh Divi 732-829-7958 | 4/23/14 confirmed Hector and/or Ramesh. Also need access to the building during the Fusion and SAP interfaces deployment on May 3rd/4th and May 10th/11th weekend?
SAP team - Ziya and Bret | On Call entire Prod cutover | Tom Wirth | Ziya Khan: 516-232-7823 Bret Weiss: 631-807-6552 | 5/14/14 from Bret . Please add Ziya to the step you have for me at 10:30 am Saturday morning as I am not available at that time. Ziya is available at 10:30 until 12, at which point I should be available.
SAP Basis team - One dedicated resource | On Site entire Prod cutover | Tom Wirth | Kazi Ahmed 516 408 8446 Shylendra Mohan 516 712 5473
SFDC technical - Nidhi | On-site Pre-cutover and cutover | Tom Wirth | Nidhi Sharma 516.734.3682 nssnidhi1@gmail.com
SFDC technical - Nishant and Khaja | On Call entire Cutover | Jomy Molakan | Khaja Moizuddin 571-422-1884 Nishant Jadav 912-441-0880 | May also be required to support QA PVT acess requirements to Salesforce for production cutover
SAP Materials - Unchin Chung and Ellen Witrick | On Call entire Cutover | Ellen Witrick |  | For SAP Interfaces which is part of the CRM Phase 1 resources required but not fusion interfaces
SAP Contracts - Tracy Drechsler | On Call, Required as data is flowing to Salesforce for Contracts | Ellen Witrick |  | For Contracts Interface part of CRM Phase 1 cutover
CRM Business Solutions Team – Mohamed, Nancy, Zishan, Suzette, Mack | On Call (Zishan entire cutover, all others -Required as data is flowing to Salesforce for validation | Mohamed Al-Daqa | Mohamed Al-Daqa: 908-240-6109 Nancy Johnson: 516-474-1919 Zishan Razzaq: 516-319-6189 Suzette Surianni: 516-282-6840 Mack Meas: 917-881-3976 | On-site preferred as feasible
Business: Sales – Adam Adler and Cliff Lavergne, Support – Blake Markham, Implementation – Robert Romines, Canada – Jeff Gallon | Monday | Mohamed Al-Daqa, Blake, Robert, Jeff, Adam, Cliff |  | Confirmed not required
Fusion/Canada PM support – Ed Maelia / Mike Wassef | On Call entire time | Ed Maelia Mike Wassef | Ed Maelia 516-658-8513 or 516-594-0251 | 5/1/14 Mike W confirmed Fernando will support At the 4/25 meeting, cutover team confirmed to include Fusion/Canada PM in case issues arise that will require their support.
Silverline - Scott | On-Site entire time | Scott Von Schilling | Scott Von Schilling | 4/15/14 as per scott he will be on call for the prod cutover and confirmed ok
BI team | On-Site for data validation | Geetha | Geetha Raman 516 974 9762
Silverline - Tom | Not Required | Tom Del Otero | Tom Del Otero | 4/22/14 Not required to have Tom. 4/22/14 will be on call
NOC - Daniel Russo – To Confirm if needed | On Call entire time | Daniel Russo | DTSupport Send Email | On NOC Calendar - No new systems going live - Jomy to confirm if needed