## Sheet1
Synergy CRM SF Phase 1 Re-implementation Required Resources Production Cutover 5/16-5/18 (See also Synergy CRM SF Phase 0a Fusion/SAP/SF Required Resources)
Required Resources | Required Availability | Confirmed By | Confirmed Resource and Phone Number | Notes
CRM Business Solutions Team – Mohamed, Nancy, Zishan, Suzette, Mack | On-Call and On Site Entire time | Mohamed Al-Daqa | Mohamed AlDaqa: 908-240-6109 Nancy Johnson: 516-474-1919 Zishan Razzaq: 516-782-3518 Suzette Suriani: 516-282-6840 Mack Meas: 917-881-3976 Ed Tateosian: 516-673-6177 | On Site Sun Day - On-Call Fri/Sat/Sun Eve Nancy to PVT accounts and contacts (US record counts, data validation between Fusion, SAP, SF) on Sat after interfaces are complete All others to PVT Salesforce key functions
CRM Silverline team - Tom, Irene, Scott | On-Call Entire time | Silverline Tom D | Tom DelOtero 201-403-3191 Scott Vonschilling Irene Starygina 718-619-2266 | Silverline will be on-call
Business Team: Sales – Adam Adler, Support – Blake Markham, Implementation – Robert Romines, Canada – Jeff Gallon | On-Site (or On-Call) Sun 9:00am - 5:00 pm for PVT and next steps. On-Call all other times | Adam, Blake, Robert, Jeff | Adam Adler: 516-734-3735 Robert Romines: 214-789-3782 Blake Markham: 801-558-8249 Jeff Gallon: 416-528-5947 | Adam to PVT Lead to Opp, Opp, alert panel (no fusion but check a few dealers and confirm alerts are there), competitive, activities, Contracts end to end with MQA Blake to PVT support processes Robert to PVT Implementation processes (SF and PSA) Jeff to PVT accounts (Nancy to provide details), and Sales/Support processes as it pertains to Canada
Business: Marketing - Mitch Bliss, Jason Barrie | On-Site (or On-Call) Sun 9:00am - 5:00pm for PVT and next steps. On-Call all other times | Steve Arentzoff Jason Barrie | Mitch Bliss 516.749.1993 | Mitch to PVT Leads, Lead Conversions PVT (includes import), web forms
Business: CPQ Sales – Cliff Lavergne | On-Site (or On-Call) Sun 9:00am - 3:00pm for PVT. On-Call all other times | Cliff Lavergne | Cliff Lavergne: 931-249-6186 | Cliff to PVT CPQ processes
Business: Telephony- Jason Fowler | On-Call Sun 9:00am - 3:00pm for PVT | Jason Fowler | Jason Fowler (281) 682-7457 | To PVT telephony integration
Business: SAP Contracts - Tracy Drechsler, Ellen Witrick | On-Site (or On-Call) Sun 9:00am - 5:00pm for PVT and next steps. On-Call all other times | Ellen Witrick | Tracy Drechsler Ellen Witrick 516-428-1558 | To confirm contracts work (to create or update contract on sun and make sure goes to SF).
Business: Lender Team | On-Site (On-call if not possible) Sun 9:00am - 3:00pm for PVT | Peter Puttagio, Jon Campbell |  | For PVT of lender team salesforce processes to confirm it is working as expected and join the bridge to confirm results and/or alert of any issues
Business: Product Team | On-Site (On-call if not possible) Sun 9:00am - 3:00pm for PVT | Sharon, Bill, Diane, Kathleen | Jessica Capocy 8137131005 | For PVT of product team salesforce processes to confirm it is working as expected and join the bridge to confirm results and/or alert of any issues
SFDC technical - Jomy, Nidhi, Nishant and Khaja | On-Site/On Call entire time | Tom Wirth | Tom Wirth: 516-244-3209 Jomy Molakan: 516-637-9111 Nidhi Sharma 516.734.3682 Khaja Moizuddin 571-422-1884 Nishant Jadav 912-441-0880 | To support the cutover and pvt activities
Synergy CRM PM - Joanne | On-Site Sun 9:00am-5:00. On Call all other times |  | Joanne Scutaro 631-821-5930
JIRA team - Vikas, Stacy Fujit | On-Site or On Call Sat for deployment and PVT | Vikas | Vikas Basra 718.304.4988 | 5/14/14 Vikas is also working with Arijit Banerjee, Shayne Pinto, Kiran Muthoju, Nagasrinivas Kumar Thaduvai (Nagasrinivas.Thaduvai@ness.com) To deploy updates for Jira interface and complete PVT in production
DTX team - Tom Sage | On-Site or On Call Sat for deployment and PVT | Tom Sage | Tom Sage 972-416-0127 | To deploy updates for DTX interface and complete PVT in production
AAX team - Trey | On Call Sun to deploy and PVT | Trey | Not Required | To deploy updates for AAX interface and complete PVT in production
BI team - Geetha, Beata, BI Consultants, DB | On-Site or On-Call Sat for BI deployment and PVT. On-call all other times | James Murphy | Binu Kinat 917-886-2807 Nagireddy Kamatam 201 654 1762 | 5/13/14 utilization updates will happen post go live 5/7/14 Nagireddy and Binu will support the go live BI deployment as per Jim To deploy BI updates and complete PVT test (key reports and dashboards) in production
PSA Team: CLD and Robert Romines | On Call Sat to deploy and initial PVT test. On Call Sun 9:00am - 3:00pm for PVT | CLD, Robert | Robert Romines 214-789-3782 CLD Primary Galen Mayfield cell: 240-415-8007 CLD BU: John Schuler cell: 410-841-4828 | To deploy PSA updates and complete PVT test in production
Web Team: Jim/Luke Karbyn | On Call Sat to deploy and PVT test. On Call all other times | Steve Arentzoff | Luke LaReau 518.281.1254 | To deploy web site form updates and complete PVT in production
QA – Margaret and/or Helen | On-Site/On-Call for interfaces and End to end Contract PVT Sun 9:00am - 3:00pm | Andrew Quattropani | Helen Rastelli: Cell 917-601-9598 Margaret Valenti: Cell-631-404-8811 | 5/15/14 Margaret will support. 3/27/14 Andrew confirmed QA will be available - will get back on specific names. Need QA team to perform PVT after deployment of each interface. To also validate asset for contract not created in SAP and contract created in SAP using report from Nidhi which will be created in production
Salesforce Premier Support | On-Call entire time
PMO - Keith Duddy | On Site Sun 9:00am - 5:00pm | Keith | Keith Duddy | To track and monitor PVT log
DT.COM - Srini Kanuri (or someone from his team) | On-Call entire time | Srini K |  | See Synergy CRM SF Phase 0a Required Resources
Canada DT.CN and DB - Paul Bird, Fernando DaSilva?? | On Call entire time | Paul Bird | Paul Bird | See Synergy CRM SF Phase 0a Required Resources
US DB Fusion Hub Oracle and Spoke SQLServer and SSIS support - Ralph Padula to assign | On-Call entire time | Ralph Padula |  | See Synergy CRM SF Phase 0a Required Resources One Fusion Hub DB and One SQL DB - Alice/Joseph?
Infrastructure - Will Tisdale, Joe Trinceri | On Call entire Prod Cutover | Charles Mahlmeister |  | See Synergy CRM SF Phase 0a Required Resources
Security - SAP | To support QA PVT Access requirements for Prod cutover | Hector Vale |  | See Synergy CRM SF Phase 0a Required Resources
SAP Basis team - One dedicated resource | On Call entire Prod cutover | Tom Wirth |  | See Synergy CRM SF Phase 0a Required Resources